## Portfolio Summary
GOLIATH Portfolio Report — February 26, 2026
Project | MW DC | Contractor | Overall Float | COD/SC Target | Risk Level | Phase
Blackford Solar | 211.21 | White/MasTec | -53 | Aug 6, 2026 | HIGH | Active Construction
Duff Solar | 138 | White/MasTec | -158 | Jul 21, 2026 | EXTREME | Active Construction
Pecan Prairie North | 407 | Wanzek | -84 | Sep 9, 2027 | MODERATE | Early Construction
Pecan Prairie South | 188 | Wanzek | -10 | May 10, 2027 | LOW-MOD | Early Construction
Scioto Ridge | — | — | — | — | NO DATA | Data Error (Blackford dupes)
Union Ridge | — | — | — | — | NO DATA | No Schedule Uploaded
Salt Branch | — | — | — | — | NO DATA | No Schedule Uploaded
Delta Bobcat | — | — | — | — | NO DATA | No Schedule Uploaded
Tehuacana | — | — | — | — | NO DATA | No Schedule Uploaded
Three Rivers | — | — | — | — | NO DATA | No Schedule Uploaded
Mayes | — | — | — | — | NO DATA | No Schedule Uploaded
Graceland | — | — | — | — | NO DATA | No Schedule Uploaded
Duffy BESS | — | — | — | — | NO DATA | No Schedule Uploaded

## Blackford Milestones
GOLIATH Portfolio Report — February 26, 2026
Milestone | Contract Date | Forecast Date | Float (Days) | Status
Backfeed/Interconnect | Jan 19, 2026 | Jun 1, 2026 | -94 | CRITICAL
HV Works Completion | Jan 19, 2026 | Jun 1, 2026 | -94 | CRITICAL
1st Circuit MC | Nov 20, 2025 | Mar 25, 2026 | -79 | CRITICAL
2nd Circuit MC | Dec 18, 2025 | Apr 13, 2026 | -17 | Behind
3rd Circuit MC | Jan 20, 2026 | Apr 27, 2026 | -25 | Behind
4th Circuit MC | Feb 10, 2026 | May 7, 2026 | -31 | Behind
5th Circuit MC | Mar 5, 2026 | May 21, 2026 | -38.5 | Behind
6th Circuit MC | Mar 26, 2026 | Jun 2, 2026 | -44 | Behind
7th Circuit MC | Apr 16, 2026 | Jun 10, 2026 | -48 | Behind
8th Circuit MC | Apr 29, 2026 | Jun 18, 2026 | -52 | Behind
Project MC | — | Jun 19, 2026 | -20 | Behind
COD | Jun 5, 2026 | Aug 6, 2026 | -53 | CRITICAL
Substantial Completion | Jun 5, 2026 | Aug 6, 2026 | -53 | CRITICAL
Final Completion | Jul 6, 2026 | Sep 18, 2026 | -53 | CRITICAL

## Duff Milestones
GOLIATH Portfolio Report — February 26, 2026
Milestone | LD Date | Forecast Date | Float (Days) | Status
HV Completion | Oct 30, 2025 | Jan 8, 2026 | — | COMPLETE
1st Circuit MC | Oct 23, 2025 | Apr 14, 2026 | -117 | CRITICAL
2nd Circuit MC | — | May 27, 2026 | -147 | CRITICAL
3rd Circuit MC | Nov 5, 2025 | Jun 24, 2026 | -158 | CRITICAL
1st Circuit Energization | — | May 29, 2026 | -116 | CRITICAL
2nd Circuit Energization | — | Jun 19, 2026 | -126 | CRITICAL
3rd Circuit Energization | — | Jun 26, 2026 | -125 | CRITICAL
1st Circuit Turnover | Jan 22, 2026 | Jun 25, 2026 | -117 | CRITICAL
2nd Circuit Turnover | — | Jul 13, 2026 | -118 | CRITICAL
3rd Circuit Turnover | Feb 2, 2026 | Jul 20, 2026 | -118 | CRITICAL
Substantial Completion | Feb 6, 2026 | Jul 21, 2026 | -115 | CRITICAL
Final Completion | — | Aug 18, 2026 | 0 | On Track

## Pecan Prairie Milestones
GOLIATH Portfolio Report — February 26, 2026
Site | Milestone | Contract Date | Forecast Date | Status
North | Mobilization | — | Sep 29, 2025 | COMPLETE
North | Backfeed Available | — | Oct 30, 2026 | Future
North | Substation Energization | Nov 24, 2026 | Nov 25, 2026 | On Track
North | MC 250 MW AC | Dec 31, 2026 | Mar 5, 2027 | Watch (-63d)
North | Full MC | Feb 19, 2027 | May 13, 2027 | Watch (-83d)
North | Substantial Completion | Apr 30, 2027 | Jul 23, 2027 | Watch (-84d)
North | COD/Final Acceptance | Jun 17, 2027 | Sep 9, 2027 | Watch (-84d)
South | Mobilization | Sep 29, 2025 | Mar 2, 2026 | Delayed
South | T-Line Energization | Nov 17, 2026 | Jan 7, 2027 | Watch
South | MC | Mar 12, 2027 | Mar 22, 2027 | On Track
South | Substantial Completion | Apr 30, 2027 | May 10, 2027 | On Track
South | Final Completion | May 28, 2027 | Jun 30, 2027 | On Track