## Action Items
ID | Date | Description | Status | Project
338 | 2026-03-02 | Bot restarted with specialist brain follow-up engine, evening date fix, WAL health check, Monday Prep label, spam removal | Open | general
316 | 2026-03-01 | Web platform streaming + markdown formatting rebuilt — needs user testing to confirm smooth performance | Open | general
305 | 2026-03-01 | Web chat streaming fully working — real-time text deltas, file access, session persistence all verified | Open | general
302 | 2026-03-01 | Web platform chat brain built — Claude CLI wrapper with persistent sessions, SSE streaming, --resume support | Open | general
301 | 2026-03-01 | Need Anthropic API key (sk-ant-api) to activate web chat brain — backend already wired, just needs the key | Open | general
298 | 2026-03-01 | File Explorer feature built and deployed — browse, upload, download, mkdir all working | Open | general
297 | 2026-03-01 | Web platform UI rebuilt with Opus 4.6 + shadcn/ui — needs user review and feedback | Open | general
294 | 2026-03-01 | Cloudflare tunnel running for web platform — temporary URL, needs permanent solution | Open | general
292 | 2026-02-28 | Goliath web platform MVP is live at http://178.156.152.148:3001 — needs chat brain wiring, auth, and systemd service installation | Open | general
290 | 2026-02-28 | Meeting invite detection pipeline built — needs testing with real invite email to verify PA forwards calendar invites | Open | general
285 | 2026-02-28 | Add "Suggested Follow-Ups" section to daily morning report PDF — contact-aware, copy-paste-ready email drafts | Open | general
286 | 2026-02-28 | Recall AI integration step-by-step guide created — saved to /opt/goliath/docs/recall-ai-integration-guide.md | Open | general
277 | 2026-02-28 | Build Recall AI integration — connect to Outlook calendar, auto-populate project contact lists from meeting attendees | Open | general
269 | 2026-02-28 | Resent welding sub email to Juan Soto with Mason McDonald and Dyami Roman-Sosa properly CC'd | Open | Mayes
265 | 2026-02-28 | Sent welding sub follow-up email to Juan Soto — CC'd Mason McDonald & Dyami Roman-Sosa — awaiting response on CRT/CET status | Open | Mayes
238 | 2026-02-28 | 13 duplicate constraints deleted from ConstraintsPro — cleanup complete | Open | general
231 | 2026-02-28 | Fix morning report date bug — uses stale/hardcoded dates instead of dynamic current date | Open | general
232 | 2026-02-28 | Build email-to-resolution pipeline — parse inbound emails for constraint resolution signals and auto-update ConstraintsPro | Open | general
233 | 2026-02-28 | Wire heartbeat service to auto-resolve matching action items in memory when constraints close in ConstraintsPro | Open | general
234 | 2026-02-28 | Consolidate morning reports into single digest — eliminate report flood | Open | general
208 | 2026-02-28 | Workspace cleaned — 4 duplicate files deleted, 3 scripts moved to /opt/goliath/scripts/, report_writer prompt fixed to prevent future misplacement | Open | general
202 | 2026-02-27 | All 8 Delta Bobcat Feb 27 call constraints synced to ConstraintsPro — 2 created, 4 updated, 2 already resolved | Open | Delta Bobcat
194 | 2026-02-27 | James Kelly to reconcile Shoals AG electrical material deliveries vs full order by Mon/Tue Mar 2-3 | Open | Delta Bobcat
195 | 2026-02-27 | Ary Mathews to gather substation/JFE delay details from Rich — potential new constraint for next meeting | Open | Delta Bobcat
196 | 2026-02-27 | Daliah Deloria to submit T&M ticket for Rt 247 road repair (2/28) + get asphalt paving quote for Nextera | Open | Delta Bobcat
197 | 2026-02-27 | Pile caps short ~30 needed for one inverter — Kyan expedite pending, ~4 weeks from execution — no positive response yet | Open | Delta Bobcat
198 | 2026-02-27 | Tariff cost increases ($5M Shoals + GameChange) being escalated to Nextera SVP Mike Flynn — keep tracking | Open | Delta Bobcat
185 | 2026-02-27 | All 8 Scioto Ridge Feb 27 call constraints synced to ConstraintsPro — 7 updated, 1 created, 0 duplicates | Open | Scioto Ridge
176 | 2026-02-27 | Pushed 8 constraints from Feb 27 call to ConstraintsPro — 1 closed, 1 escalated, 4 updated, 2 new created | Open | Scioto Ridge
172 | 2026-02-27 | Luis to email Gomez (Stantec) re: DMC connectors / grounding material — flagged HIGH priority | Open | Scioto Ridge
173 | 2026-02-27 | Substation secondary power RFI blocked — RWE owes studies to Ohio Mid utility, ~2 month delay | Open | Scioto Ridge
170 | 2026-02-27 | 13 action items from Feb 27 constraints call — track Luis on DMC connectors, Sahil on substation RFI clarification, DC electrical start Mar 2 | Open | Scioto Ridge
163 | 2026-02-27 | Blackford HIGH priority probing questions report generated — 5 constraints, 15 questions, 4 follow-up email drafts | Open | Blackford
161 | 2026-02-27 | Generating high-priority probing questions report for Blackford — user requested meeting prep doc | Open | Blackford
160 | 2026-02-27 | Recall.ai integration built and committed (c806110) — awaiting bot restart to go live | Open | general
155 | 2026-02-27 | Build contact/name-to-project mapping table for email→ConstraintsPro routing | Open | general
156 | 2026-02-27 | Full build queue established — 8 features prioritized for autonomous operation | Open | general
151 | 2026-02-27 | Reliability overhaul shipped — 1800s timeout, 300s per-subagent with retry, Telegram timeouts, heartbeat, partial failure handling | Open | general
149 | 2026-02-27 | Filed 4 schedule PDFs from Gmail — Salt Branch + Three Rivers new, Blackford x2 duplicates skipped | Open | general
148 | 2026-02-27 | Probing questions workflow fully implemented in codebase — agent prompts + orchestrator updated | Open | general
143 | 2026-02-27 | Salt Branch constraint questions PDF emailed to bandicoot.hg@gmail.com for call prep | Open | Salt Branch
142 | 2026-02-27 | Build schedule PDF auto-filing in email pipeline — detect project, save to projects/<key>/schedules/, notify user | Open | general
138 | 2026-02-27 | Build proactive outbound email capability (parked — user lacks PA webhook access) | Open | general
98 | 2026-02-26 | Flow #3 expanded — full transcript analysis for ALL calls (constraints, action items, commitments, coaching, proactive suggestions) | Open | general
94 | 2026-02-26 | User wants Teams calendar integration via Power Automate — daily sync of meetings, attendees, roles, contact info | Open | general
95 | 2026-02-26 | Feature request: Post-meeting transcript analysis for automatic constraint extraction via Power Automate Flow #3 | Open | general
92 | 2026-02-26 | User wants Teams calendar integration via Power Automate — daily sync of meetings, attendees, roles, contact info | Open | general
62 | 2026-02-26 | Off-site storage cost tracker sent to Tanner Thatcher — awaiting cost estimates | Open | Three Rivers
58 | 2026-02-26 | First Solar coordination call agenda PDF created — ready for Tanner Thatcher to schedule | Open | Three Rivers
56 | 2026-02-26 | New high-priority constraint created — Module Delivery Staging, due March 5, owner Tanner Thatcher | Open | Three Rivers
45 | 2026-02-26 | Salt Branch constraint follow-ups identified for Feb 26 — Wire Mgmt due today, Turnover Docs + Sanderfoot due tomorrow, Cast-in-place due Feb 28 | Open | Salt Branch
23 | 2026-02-25 | User building constraint tracker API endpoint and Power Automate flows — waiting on delivery | Open | general
13 | 2026-02-25 | Waiting on user to collect APM responses to 14 constraint action items — expect updates in 4-5 hours | Open | Pecan Prairie
11 | 2026-02-24 | Generated 47 schedule pressure-test questions (23 North, 24 South) from Level 3 detailed schedules | Open | Pecan Prairie

## Project Health
Project | Constraints Open | Schedule Status | Key Risk
Union Ridge | 0 | On Track | None identified
Duff | 0 | On Track | None identified
Salt Branch | 0 | On Track | None identified
Blackford | 0 | On Track | None identified
Delta Bobcat | 0 | On Track | None identified
Tehuacana | 0 | On Track | None identified
Three Rivers | 0 | On Track | None identified
Scioto Ridge | 0 | On Track | None identified
Mayes | 0 | On Track | None identified
Graceland | 0 | On Track | None identified
Pecan Prairie | 0 | On Track | None identified
Duffy BESS | 0 | On Track | None identified

## Constraint Movement
Project | New | Resolved | Aging (>14d) | Critical